## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (WEEK)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1. PLANNING
A) TEAM SETUP & MEETING | 1 | 1 | 1 | 1 | bar: PERIODS (WEEK) 1
B) IS PROJECT IDENTIFICATION | 1 | 1 | 1 | 1 | bar: PERIODS (WEEK) 1
C) IS CLIENT IDENTIFICATION | 2 | 1 | 1 | 1 | bar: PERIODS (WEEK) 1
D) REQUIREMENT COLLECTION | 2 | 2 | 2 | 2
E) SDP SUBMISSION | 3 | 1 | 3 | 1
2. ANALYSIS
A) PRODUCE ERD | 3 | 2 | 3 | 2
B) PRODUCE IS DFD | 3 | 2 | 3 | 2
C) ERD AND DFD VERIFICATION WITH LECTURER/SUPERVISOR AND CLIENT | 3 | 2 | 3 | 2
D) SRS SUBMISSION | 4 | 1 | 4 | 1
3. DESIGN
A) FINAL ERD VERIFICATION | 5 | 1 | 5 | 1
B) FINAL DFD VERFICATION | 5 | 1 | 5 | 1
C) DESIGN INTENDED UI | 5 | 1 | 5 | 1
D) PRODUCE MASTER UI | 5 | 1 | 5 | 1
E) SDD SUBMISSION | 5 | 1 | 5 | 1
4. IMPLEMENTATION
A) START CODING THE SYSTEM | 5 | 7 | 5 | 7
B) CONDUCT UNIT AND INTEGRATION TEST | 6 | 7 | 6 | 7
C) CONDUCT SYSTEM TEST | 13 | 1 | 13 | 1
D) CONDUCT UAT (CLIENT) | 14 | 1 | 14 | 1
5. MAINTENANCE
A) BUGS FIXING AFTER SYSTEM TEST | 13 | 1 | 13 | 1
B) BUGS FIXING AFTER UAT | 14 | 1 | 14 | 1